## Stakeholder Register
Stakeholder Matrix
Loan Portfolio Risk Reporting Dashboard — Harvest Trust Financial (HTF)
Phase 2 of 7: | Stakeholder Analysis (Stakeholder Matrix)
Prepared By: | Dwij Siyal
Version: | 1.0.
Date: | 2026-08-01
Stakeholder / Role | Department | Power | Interest | Quadrant | Key Needs from the Dashboard | Key Concerns / Pain Points | Engagement Strategy
Chief Risk Officer (CRO) | Executive / Risk Management | High | High | Manage Closely | Portfolio-level risk exposure trends; concentration risk by region/sector; confidence the dashboard reflects true risk. | Being blindsided by a risk event the old manual reports didn't surface in time. | Involve in brief/requirements sign-off; brief on key milestones; final go-live approval.
VP, Credit & Lending Operations | Credit / Lending | High | High | Manage Closely | Delinquency by branch/loan officer; a prioritized watch-list of at-risk loans. | Inconsistent risk-tier definitions undermining lending decisions; slow escalation of problem accounts. | Co-owns requirements; reviews and signs off on definitions and dashboard design.
Regional Credit Managers (SK / AB / MB) | Credit / Lending — Regional | Medium | High | Keep Informed | Region-level delinquency and sector concentration (e.g., grain vs. livestock exposure) for their territory. | Losing visibility into their own region's risk between monthly report cycles. | Consult during requirements gathering; give early preview/demo before go-live to build buy-in.
Portfolio Risk Analysts | Risk Management | Medium | High | Keep Informed | Granular, slice-able data: risk tier, days-past-due bucket, LTV, sector, region — the detail behind every KPI. | Currently own the manual reporting burden; worried a new tool won't cover an edge case they handle by hand today. | Primary working group for requirements and UAT; treat as co-designers, not just end users.
Finance & Treasury | Finance | High | Medium | Keep Satisfied | Aggregate portfolio exposure and risk-tier mix to inform Allowance for Credit Losses (ACL) estimates. | Numbers in the dashboard not reconciling with figures used in financial reporting. | Periodic high-level updates; confirm definitions align with financial reporting standards.
Internal Audit & Compliance | Audit / Compliance | High | Medium | Keep Satisfied | Confidence in data lineage, consistent definitions, and an auditable trail from source data to dashboard figure. | A dashboard that looks good but can't be traced back to source data if questioned. | Consult on data lineage/traceability requirements; review before go-live, not day-to-day.
IT / Data Team | Information Technology | Low | Low | Monitor | Clear, stable data source requirements and a manageable refresh schedule. | Being asked to support a tool with undocumented or shifting data requirements. | Inform of data/refresh requirements early; involve only when technical dependencies arise.

## Power-Interest Matrix
Power / Interest Matrix
Engagement strategy by stakeholder influence and level of interest
| Phase 2 of 7: | Stakeholder Analysis (Power / Intrest Matrix)
| Prepared By: | Dwij Siyal
| Version: | 1.0.
| Date: | 2026-08-01
INTEREST ▲
HIGH | KEEP INFORMED (Low Power / High Interest) • Regional Credit Managers (SK/AB/MB) • Portfolio Risk Analysts |  | MANAGE CLOSELY (High Power / High Interest) • Chief Risk Officer • VP, Credit & Lending Operations
LOW | MONITOR (Low Power / Low Interest) • IT / Data Team |  | KEEP SATISFIED (High Power / Low(er) Interest) • Finance & Treasury • Internal Audit & Compliance
| LOW POWER |  | HIGH POWER
POWER / INFLUENCE ►

## RACI Chart
RACI Chart
R = Responsible A = Accountable C = Consulted I = Informed
Phase 2 of 7: | Stakeholder Analysis (RACI chart)
Prepared By: | Dwij Siyal
Version: | 1.0.
Date: | 2026-08-01
Activity | Business Analyst (Dwij Siyal) | Chief Risk Officer | VP Credit & Lending Ops | Regional Credit Mgrs | Portfolio Risk Analysts | Finance & Treasury | Internal Audit & Compliance | IT / Data Team
Approve project brief & scope | R | A | C | I | I | I | I | I
Define business/functional/non-functional requirements | R | I | A | C | C | C | I | I
Define risk tier & delinquency bucket definitions | R | I | A | I | C | C | C | I
Provide source data & data access | C | I | I | I | I | I | I | R/A
Design data model | R/A | I | I | I | C | I | I | C
Build Power BI dashboard | R/A | I | I | I | C | I | I | I
Test & validate dashboard accuracy (UAT) | R | I | C | C | A | I | C | I
Sign off for go-live | R | A | C | I | C | I | C | I
Ongoing refresh & maintenance | C | I | A | I | I | I | I | R
R | R R C: Responsible: does the work
A | R R C: Accountable: owns the outcome, signs off (one per activity)
C | R R C: Consulted: gives input before the work is done
I | R R C: Informed: told after the fact